Work Plan for the APT Preparatory Group for the ITU Plenipotentiary Conference 2026

Adopted at

The 2nd Meeting of the APT Preparatory Group for the ITU Plenipotentiary Conference 2026

28 - 29 January 2026, Fully Virtual Meeting

| Year | Date/venue | APT activities | ITU activities | Actions |
| --- | --- | --- | --- | --- |
| 2025 | 10–21 February 2025 Geneva, Switzerland |  | Cluster of Council Working Groups, Expert Groups and Informal Expert Group | - Follow up the outcomes |
|  | 7–11 July 2025 Geneva, Switzerland |  | WSIS+20 High-Level Event 2025 | - Follow up the outcomes |
|  | 7–17 June 2025 Geneva Switzerland |  | 2025 Session of the Council | - Follow up the outcomes |
|  | 18 July 2025 Pattaya, Thailand | 1st Meeting of the APT Preparatory Group for PP-26 (APT PP26-1) |  | - Election of Chair/Vice-Chairs - Setup of Structure - Appointment of WG Chairs/Vice-Chairs - Consideration of the Working Methods - Consideration of the Work Plan - Review the outcomes of the 2025 Session of the Council |
|  | 8–19 September 2025 Geneva, Switzerland |  | Cluster of Council Working Groups and Expert Groups | - Follow up the outcomes |
|  | 17–28 November 2025 Baku, Azerbaijan |  | WTDC-25 | - Follow up the outcomes |
| 2026 | 12–23 January 2026 Geneva, Switzerland |  | Cluster of Council Working Groups and Expert Groups | - Follow up the outcomes |
|  | 13 January 2026 Geneva, Switzerland |  | First Informal Inter-Regional Preparatory Meeting for PP-26 | - Provide APT’s updates - Follow the updates from ITU and other regions |
|  | 28–29 January 2026 (2 working days) Fully Virtual | 2nd Meeting of the APT Preparatory Group for PP-26 (APT PP26-2) |  | - Consideration of the input contributions from APT Members - Review the outcomes of the preparatory process of other regional organizations - Consideration of the Issue Papers prepared by the Working Groups of APT PP-26 - Develop APT Views on PP-26 issues - Review the outcomes of WTDC-25 - Review the outcomes of Council Working Groups and Expert Groups |
|  | 26–28 March 2026 (3 working days) Bangkok, Thailand | APT Training Course on Preparation for Plenipotentiary Conference 2026 |  | - Provides an opportunity to experience discussion, negotiation, and coordination on issues at international conferences. |
|  | 30 March–2 April 2026 (4 working days) Bangkok, Thailand | 3rd Meeting of the APT Preparatory Group for PP-22 (APT PP22-3) |  | - Consideration of the input contributions from APT Members - Review the outcomes of the preparatory process of other regional organizations - Develop Preliminary APT Common Proposals for PP-26, if any - Consideration of the revised Issue Papers from the Working Groups of APT PP-26 - Develop APT contributions, if any, to 2026 Session of the Council |
|  | 27 April 2026 (TBD) Geneva, Switzerland |  | Joint meeting of CWG-SFP and CWG-FHR | - Follow up the outcomes |
|  | 28 April–8 May 2026 Geneva, Switzerland |  | 2026 Session of the Council | - Follow up the outcomes |
|  | 30 April 2026 Geneva Switzerland |  | Second Informal Inter-Regional Preparatory Meeting for PP-26 | - Provide APT’s updates - Follow the updates from ITU and other regions |
|  | 8–11 June 2026 Nassau, Bahamas |  | WTPF-26 | - Follow up the outcomes |
|  | 10 June 2026 Nassau, Bahamas |  | Third Informal Inter-Regional Preparatory Meeting for PP-26 | - Provide APT’s updates - Follow the updates from ITU and other regions |
|  | 15–19 June 2026 (5 working days) Kuala Lumpur, Malaysia | 4th Meeting of the APT Preparatory Group for PP-26 (APT PP26-4) |  | - Consideration of the input contributions from APT Members - Review outcomes of the preparatory process of other regional organizations - Develop Preliminary APT Common Proposals for PP-26, if any - Consideration of the revised Issue Papers from the Working Groups of APT PP-26 - Review the outcomes of Council 2026 - Review the outcomes of WTPF-26 - Special sessions for the ITU PP-26 Election Campaign |
|  | 6–10 July 2026 Geneva, Switzerland |  | WSIS 2026 | - Follow up the outcomes |
|  | 24–28 August 2026 (5 working days) Brisbane, Australia | 5th Meeting of the APT Preparatory Group for PP-26 (APT PP26-5) |  | - Consideration of the input contributions from APT Members - Review the outcomes of the preparatory process of other regional organizations - Develop Preliminary APT Common Proposals for PP-26 - Develop necessary procedures and arrangements for APT coordination meetings - Special sessions for the ITU PP-26 Election Campaign |
|  | September-October 2026 | Process of ACPs |  | - Circulation of PACPs - Finalization of ACPs - Submission of ACPs to ITU PP-26 |
|  | 14-15 October 2026 (TBD) Riyadh, Saudi Arabia |  | Fourth Informal Inter-Regional Preparatory Meeting for PP-26 | - Provide APT’s updates - Follow the updates from ITU and other regions |
|  | 7 November 2026 Doha, Qatar |  | Final meeting of the 2026 session of the Council | - Follow up the outcomes |
|  | 9–27 November 2026 Doha, Qatar | APT Coordination Meetings at PP-26 | PP-26 | - Ensure that the APT Common Proposals are well reflected in the proceedings of PP-26 - Coordinate views with other regional organizations and take necessary actions to promote APT’s interests. - Follow up the outcomes |
|  | 27 November 2026 Doha, Qatar |  | Extraordinary Session of the 2027 Council | - Follow up the outcomes |

Important Deadlines:

- Deadline for submission of proposals to amend the Constitution and Convention (CS/CV) to ITU: 9 March 2026

- Deadline for submission of other proposals to ITU: 9 July 2026

- Firm deadline for submission of all contributions to ITU: 19 October 2026